## START HERE
SAGE Fall Detection: FYP Continuation Plan
Section | What this workbook is for
Why this exists | The original 3-Week AI Workflow got SAGE to a working MVP. The project has since grown into a real research effort: hybrid AI architecture, TCN vs LSTM comparison, explainability, and edge deployment. This workbook is the continuation, not a replacement — keep the original file for the MVP history.
Structure | 8 phases across roughly weeks 4-12. Each phase has its own tab with tasks, owners, and deliverables. Weeks 7 (TCN vs LSTM) and 8 (Hybrid AI) get their own deep-dive tabs since they are the core research contribution.
Team names | Fatima, Sanawar, Hussain
Relationship to old workbook | The 'Advanced Features Later' sheet from the original file (medication monitoring, gait analysis, nighttime monitoring, wandering detection, LIME/SHAP, etc.) stays as-is in that file. This plan focuses on core fall-detection research before those extensions.
New tracking sheets | Literature Review Tracker and Experiment Tracker are added here so your thesis writing (Phase 8) has organized source material and results instead of starting from scratch.
File design note | Same conventions as the original: wide columns, wrapped text, left alignment, no merged data cells, filterable tables.

## 8-Phase Roadmap
8-Phase FYP Roadmap (Weeks 4-12)
Continuation of the 3-week MVP plan. Update Status as each phase progresses.
Phase | Week(s) | Phase Name | Key Deliverables | Primary Focus | Status
1 | 4 | Research & Literature Review | Literature matrix (30-40 papers), comparison table, draft architecture diagram, technology selection document | Fall detection, hybrid AI, TCN vs LSTM, pose vs object detection, edge vs cloud | Not Started
2 | 5 | Dataset & Architecture Design | Finalized system architecture, pipeline diagram, dataset selection | Study open-source fall detection repos, MediaPipe vs YOLO Pose, decide pipeline shape | Not Started
3 | 6 | Baseline Model | Data preprocessing, sliding windows, training pipeline, baseline metrics | Train LSTM baseline on pose sequences | Not Started
4 | 7 | Temporal Model Comparison | TCN implementation, full TCN vs LSTM comparison report | Accuracy, recall, precision, F1, latency, parameters, memory, edge inference speed | Not Started
5 | 8 | Hybrid AI Exploration | Hybrid pipeline prototype, value assessment of LLM reasoning layer | Add object detection + LLM reasoning on top of the temporal model | Not Started
6 | 9 | Explainability & Edge Deployment | SHAP/LIME outputs, quantization results, Jetson/Raspberry Pi benchmark | Explainability + feasibility on real edge hardware | Not Started
7 | 10 | Dashboard & Integration | Caregiver dashboard, alert system, event history, explainable alerts | End-to-end integration of models into a usable app | Not Started
8 | 11-12 | Evaluation & Thesis | Confusion matrices, ROC/PR curves, ablation study, full report, presentation | Experiments, comparisons, thesis writing, defense prep | Not Started

## Phase Details
Phase Details: Weeks 4, 5, 6, 9, 10, 11-12
Weeks 7 (TCN vs LSTM) and 8 (Hybrid AI) have their own deep-dive tabs.
Phase | Week | Task | Fatima | Sanawar | Hussain | Deliverable | Status
1 | 4 | Literature review | Read + log fall detection papers into Literature Review Tracker | Read + log hybrid AI / TCN vs LSTM papers into tracker | Read + log edge deployment + explainability papers into tracker | Literature matrix (30-40 papers) | Not Started
1 | 4 | Comparative analysis | Draft TCN vs LSTM comparison table from papers | Draft pose estimation vs object detection comparison | Draft edge vs cloud architecture comparison | Comparison tables | Not Started
1 | 4 | Architecture decision | Contribute to architecture diagram | Contribute to architecture diagram | Own final architecture diagram + tech selection doc | Final architecture diagram + technology selection document | Not Started
2 | 5 | Repo research | Study 2-3 open-source fall detection repos for feature engineering ideas | Compare MediaPipe vs YOLO Pose on sample videos | Study repo structures for the redesigned pipeline | Notes on candidate repos + pose model choice | Not Started
2 | 5 | Pipeline decision | Help decide: pose only / pose+object detection / pose+TCN / pose+LSTM / hybrid+LLM | Help decide pipeline shape; document tradeoffs | Draw the complete pipeline diagram | Decision recorded + full pipeline diagram | Not Started
3 | 6 | Data preprocessing | Build feature extraction from pose sequences | Build sliding window generator | Wire preprocessing into repo structure + logging | Clean preprocessing pipeline | Not Started
3 | 6 | LSTM training | Train baseline LSTM on windows | Track training metrics (accuracy, precision, recall, F1) | Document training run + save model artifact | Trained LSTM baseline + metrics report | Not Started
6 | 9 | Explainability | Run SHAP on trained model outputs | Run LIME on trained model outputs | Summarize explainability findings for caregiver relevance | SHAP/LIME report | Not Started
6 | 9 | Edge feasibility | Test model quantization | Benchmark inference on Raspberry Pi | Benchmark inference on Jetson; compare memory/latency | Edge feasibility benchmark report | Not Started
7 | 10 | Dashboard build | Design alert + explanation UI content | Build event history + logging backend | Build dashboard shell + notification workflow | Working caregiver dashboard | Not Started
8 | 11-12 | Evaluation | Generate confusion matrices + ROC/PR curves | Run ablation study (rule-based vs LSTM vs TCN vs hybrid) | Compile results into report structure | Full evaluation package | Not Started
8 | 11-12 | Thesis & presentation | Write methodology + results sections | Write literature review + comparison sections | Write intro/conclusion + prepare slides | Draft thesis + presentation | Not Started

## Week 7 - TCN vs LSTM
Week 7 Deep Dive: TCN vs LSTM
This comparison is a core research contribution — treat it as its own mini-experiment, not a side task.
Metric | Why it matters | How to measure | Target / Notes
Accuracy | Overall correctness of fall vs no-fall classification | Held-out test split, same split for both models | Report alongside class balance; accuracy alone can hide missed falls
Recall (Sensitivity) | Missing a real fall is the costliest error for this application | TP / (TP + FN) on fall class | Prioritize this metric — a caregiver system should minimize missed falls
Precision | Too many false alarms erodes caregiver trust in the system | TP / (TP + FP) on fall class | Balance against recall; discuss the tradeoff explicitly in the thesis
F1-score | Single number balancing precision and recall | Harmonic mean of precision and recall | Use as the headline comparison number
Latency | Determines if detection is fast enough to be useful in real time | Time from input window to prediction, averaged over N runs | Measure on the same hardware for both models
Parameter count | Proxy for model size / memory footprint | Count trainable parameters | Smaller is better for edge deployment, all else equal
Memory usage (RAM) | Determines feasibility on constrained edge hardware | Peak RAM during inference | Measure on Raspberry Pi and Jetson separately (Week 9 overlap)
Edge inference speed | Real deployment target performance, not just desktop/GPU numbers | Frames-per-second or ms/window on target device | This is the number that decides deployability
Task Breakdown
Task | Owner | Status
Implement TCN architecture (dilated causal convolutions) matching the LSTM's input windows | Sanawar | Not Started
Keep train/val/test split, preprocessing, and window size identical between LSTM and TCN | Fatima | Not Started
Train TCN with same compute budget/epochs as LSTM baseline for a fair comparison | Fatima + Sanawar | Not Started
Benchmark both models on desktop/GPU for accuracy metrics | Sanawar | Not Started
Benchmark both models on target edge hardware for latency/memory | Hussain | Not Started
Write up comparison table + discussion for the thesis | All | Not Started

## Week 8 - Hybrid AI
Week 8 Deep Dive: Hybrid AI Architecture
Goal: decide whether an LLM reasoning layer adds real value (better explanations for caregivers) — not to make the LLM detect falls itself.
Pipeline Stage | Description | Tool / Model Options | Owner | Status
Camera | Raw video input | Existing OpenCV capture pipeline | Sanawar | Not Started
Pose Estimation | Extract body keypoints | MediaPipe Pose (current) vs YOLO Pose (evaluated Week 5) | Fatima | Not Started
Object Detection | Detect relevant objects in scene (e.g. furniture, floor context) | YOLO (ultralytics) | Sanawar | Not Started
Temporal Model | Classify fall / no-fall from sequences | Best model from Week 7 comparison (LSTM or TCN) | Fatima | Not Started
Structured Features | Package pose + object + temporal outputs into a structured summary | Custom feature schema (JSON/dict) | Hussain | Not Started
LLM Reasoning | Interpret structured event and produce a caregiver-friendly explanation | Small local LLM or API call, prompted on structured features only (not raw video) | Hussain | Not Started
Alert | Deliver explained alert to dashboard/notification | Dashboard from Week 10 | Hussain | Not Started
Key Decisions to Make
Question | Options | Decision Criteria
Does the LLM improve caregiver understanding enough to justify its cost/latency? | Yes, keep it / No, drop it / Yes, but only for high-severity alerts | A/B compare caregiver-readable explanation quality vs a template-based explanation
Where does the LLM run? | On-device (edge) / Cloud API / Hybrid (cheap local summary + optional cloud detail) | Depends on latency budget, privacy requirements, and internet reliability at deployment site
What is the LLM's input? | Structured features only / Structured features + short video clip description | Prefer structured-only first — simpler, faster, and avoids sending raw video externally

## Literature Review Tracker
Literature Review Tracker
Legend: fill in one row per paper. Row 6 (highlighted) is an example — delete it once you add real entries. Aim for 30-40 papers total (Phase 1 target).
Paper ID | Title | Year | Dataset | Pose Model | Temporal Model | Object Detection | LLM/VLM | Hardware | Metrics Reported | Strengths | Weaknesses | Ideas for SAGE
P001 | EXAMPLE — replace with real paper title | 2023 | UP-Fall | OpenPose | LSTM | None | None | Desktop GPU | Acc 0.94, F1 0.91 | Good accuracy on constrained dataset | Not tested on edge hardware; small dataset | Consider using their feature set as a comparison baseline

## Experiment Tracker
Experiment Tracker
Legend: log every training run here, including failed/negative results — those matter for the ablation study in Phase 8. Row 6 (highlighted) is an example.
Experiment ID | Date | Dataset | Model (Rule-based / LSTM / TCN / Hybrid) | Hyperparameters | Accuracy | Recall | F1-score | Inference Time (ms) | Notes
E001 | 2026-08-15 | UP-Fall (subset) | LSTM | window=45, hidden=64, lr=0.001, epochs=30 | 0.91 | 0.88 | 0.895 | 12 | EXAMPLE ROW — replace with real experiment results

## Progress Tracker
SAGE Progress Tracker (continued from T14)
Continues the Task ID numbering from the original 3-Week workbook.
Task ID | Task | Owner | Phase | Priority | Status | Notes
T15 | Build literature matrix (30-40 papers) | All | Phase 1 | High | Not Started
T16 | Draft TCN vs LSTM comparison table from literature | All | Phase 1 | High | Not Started
T17 | Finalize architecture diagram + tech selection doc | Hussain | Phase 1 | High | Not Started
T18 | Compare MediaPipe vs YOLO Pose | Sanawar | Phase 2 | Medium | Not Started
T19 | Draw full redesigned pipeline diagram | Hussain | Phase 2 | High | Not Started
T20 | Build preprocessing + sliding window pipeline | Fatima + Sanawar | Phase 3 | High | Not Started
T21 | Train LSTM baseline on pose sequences | Fatima | Phase 3 | High | Not Started
T22 | Implement TCN architecture | Sanawar | Phase 4 | High | Not Started
T23 | Run full TCN vs LSTM comparison (accuracy + edge metrics) | All | Phase 4 | High | Not Started
T24 | Prototype hybrid pipeline (pose + object detection + temporal model) | Fatima + Sanawar | Phase 5 | High | Not Started
T25 | Evaluate LLM reasoning layer value | Hussain | Phase 5 | Medium | Not Started
T26 | Run SHAP/LIME explainability analysis | Fatima + Sanawar | Phase 6 | Medium | Not Started
T27 | Benchmark on Raspberry Pi and Jetson | Hussain | Phase 6 | High | Not Started
T28 | Build caregiver dashboard + alert system | Hussain | Phase 7 | High | Not Started
T29 | Run ablation study (rule-based vs LSTM vs TCN vs hybrid) | All | Phase 8 | High | Not Started
T30 | Write thesis + prepare presentation | All | Phase 8 | High | Not Started