## START HERE
SAGE — Next Month Roadmap (v2: 3 weeks implementation + 1 week testing)
Companion to SAGE_FYP_Continuation_Plan.xlsx and docs/IMPLEMENTATION_PLAN.md. This version compresses implementation into Weeks 1-3 and dedicates Week 4 entirely to testing/validation, per team request.
What changed from v1 | v1 spread each branch's work + write-up evenly across 4 weeks. v2 compresses all implementation and a first-pass write-up into Weeks 1-3, and turns Week 4 into a dedicated testing/validation week -- not just a buffer, a structured set of testing activities (see 'Sync Points & Decisions' and each branch's Week 4 row).
Read this before you agree to the compression | GAIT_hussain is the branch most at risk from this change. Its task list depends on a literature review + data-availability assessment BEFORE any modeling can start -- and 'no existing dataset supports gait analysis' was already flagged as a High/High risk in v1. Losing a week of buffer means less room to discover that problem and still adjust. See the contingency noted in the GAIT_hussain Tasks tab and Risks & Blockers -- if the data situation looks bad by end of Week 1, the plan is to SCALE DOWN scope (fewer signals), not silently slip the deadline.
The three branches | TCN_sanawar (Sanawar): TCN vs LSTM comparison. YOLO_fatima (Fatima): object detection layer. GAIT_hussain (Hussain): gait analysis / fall-risk prediction.
The one rule (unchanged) | Nobody edits pipeline_utils.py, src/posture/lstm/*, hybrid_evaluate.py, evaluate_real_footage.py, or realtime_fall_detection.py during this month. New files, new folders only.
What Week 4 testing actually means | Not vague 'testing time' -- see the 4-Week Overview and each branch's Tasks tab: full validation against Testing/ clips, the Merge Checklist run for real (not just at the very end), a cross-branch compatibility smoke test (do ultralytics + TCN's Keras usage + the gait module coexist in one environment without conflicts?), and a regression check that the existing heuristic+LSTM pipeline is untouched.
File design note | Same conventions as the Continuation Plan workbook: wide columns, wrapped text, left alignment, no merged data cells, filterable tables.

## 4-Week Overview
4-Week Overview — Weeks 1-3 implementation, Week 4 dedicated testing
Week | TCN_sanawar | YOLO_fatima | GAIT_hussain | Team Sync Point
Week 1 | Understand existing LSTM feature pipeline; implement TCN architecture + trainer; first training run completed | Install ultralytics; get YOLOv8n running alongside MediaPipe; sanity-check person detection | Literature review on gait analysis / fall-risk prediction; data-availability assessment -- decide data strategy fast, this gates everything else | Kickoff: confirm branch scope + the 'no shared-file edits' rule. GAIT check-in: is the data situation workable in 3 weeks, or does scope need to shrink now?
Week 2 | Tune hyperparameters; implement tcn_classifier.py matching LSTMPostureClassifier's interface; build comparison script; begin running comparisons | Benchmark latency + accuracy over Testing/ clips; investigate medicine-container detection feasibility (COCO proxy vs. custom data need) | Define risk-score output contract; implement feature extraction AND a first-pass rule-based risk model (compressed from two separate weeks in v1) | Mid-point check-in: share early numbers, flag anything at risk of slipping into Week 4's testing time
Week 3 | Finish full TCN vs LSTM comparison (accuracy/recall/precision/F1/latency/params/memory) on Testing/Sanawar Testing 7-22-26; write up report + recommendation | Finalize detection output schema; write up findings (person-detection reliability, latency, medicine-container feasibility) | Validate risk model on available data; write up literature summary + honest limitations (compressed from two separate weeks in v1) | End of Week 3: all three implementation deliverables + first-pass write-ups due. TCN comparison results shared -- preliminary LSTM-vs-TCN direction discussed ahead of Week 4
Week 4 — TESTING | Re-run comparison to confirm results are reproducible; support merge-checklist review | Full validation across ALL Testing/ clips (not just a sample used during dev); support merge-checklist review | Final validation pass on the full available dataset; support merge-checklist review | Cross-branch smoke test (dependency compatibility check); regression check on the existing heuristic+LSTM pipeline; Merge Checklist formally signed off per branch; LSTM-vs-TCN decision finalized; Month 2 integration phase planned

## TCN_sanawar Tasks
TCN_sanawar — Task Breakdown (3 weeks implementation + 1 week testing)
Week | Task | Deliverable | Depends On | Status
Week 1 | Read lstm_features.py and lstm_dataset.py end to end | Understanding of the existing 132-dim feature/window pipeline -- no code yet | - | Not Started
Week 1 | Implement tcn_model.py: build_tcn_model(window_size, n_features, n_classes) | Dilated causal Conv1D stack, matching lstm_trainer.py's build_model() signature | Above | Not Started
Week 1 | Implement tcn_trainer.py (near-copy of lstm_trainer.py, swap model builder); first training run | First trained model: models/tcn_posture.keras | Above | Not Started
Week 2 | Tune architecture / hyperparameters for a fair comparison | Reasonable accuracy on validation split; parameter count noted | Week 1 training run | Not Started
Week 2 | Implement tcn_classifier.py mirroring LSTMPostureClassifier's interface exactly | .predict(window), .window_size, .raw_history_needed, .is_available all match | tcn_model.py | Not Started
Week 2 | Build compare_tcn_lstm.py and begin running comparisons | Script + first comparison numbers, even if not final | tcn_classifier.py | Not Started
Week 3 | Finish full comparison on Testing/Sanawar Testing 7-22-26 | Accuracy, recall, precision, F1, latency (ms/window), parameter count, peak RAM for both models | Week 2 script | Not Started
Week 3 | Write up comparison report + recommendation -- foreground recall specifically | Markdown report + one clear LSTM-or-TCN recommendation, shared with the team | Comparison results | Not Started
Week 4 -- TESTING | Re-run the comparison from a clean environment to confirm results reproduce | Confidence the numbers aren't an artifact of a one-off run | Week 3 report | Not Started
Week 4 -- TESTING | Go through the Merge Checklist tab item by item; confirm no shared files were touched | Signed-off checklist for this branch | - | Not Started
Week 4 -- TESTING | Participate in the cross-branch dependency smoke test | Confirms TCN's TF/Keras usage doesn't conflict with YOLO's ultralytics install in one environment | All branches ready | Not Started

## YOLO_fatima Tasks
YOLO_fatima — Task Breakdown (3 weeks implementation + 1 week testing)
Week | Task | Deliverable | Depends On | Status
Week 1 | Install ultralytics, download YOLOv8n pretrained (COCO) weights | Working local YOLO install | - | Not Started
Week 1 | Implement src/detection/yolo_objects.py: YOLOObjectDetector.detect(frame) -> list[dict] | Class with {class, confidence, bbox} output per detection | Above | Not Started
Week 1 | Sanity-check person detection on a few Testing/ clips | Confirms near-100% person-detection reliability given COCO pretraining | yolo_objects.py | Not Started
Week 2 | Benchmark latency: YOLO alone, and MediaPipe+YOLO together, on the dev machine | Honest per-frame ms numbers -- the real cost of adding this layer | Detector working | Not Started
Week 2 | Investigate medicine-container detection: COCO 'bottle' proxy vs. custom-trained option | Written feasibility assessment; custom dataset scoped but not necessarily started | Detector working | Not Started
Week 3 | Finalize detection output schema for later integration | Documented {class, confidence, bbox} contract | Weeks 1-2 | Not Started
Week 3 | Write up findings: person-detection reliability, latency, medicine-container feasibility | Short report, shared with the team | All above | Not Started
Week 4 -- TESTING | Run full validation across ALL Testing/ clips, not just the sample used during development | Confidence the Week 2 numbers hold up broadly, not just on a few cherry-picked clips | Week 3 report | Not Started
Week 4 -- TESTING | Go through the Merge Checklist tab item by item | Signed-off checklist for this branch | - | Not Started
Week 4 -- TESTING | Participate in the cross-branch dependency smoke test | Confirms ultralytics doesn't conflict with the other branches' dependencies | All branches ready | Not Started

## GAIT_hussain Tasks
GAIT_hussain — Task Breakdown (3 weeks implementation + 1 week testing)
Week | Task | Deliverable | Depends On | Status
Week 1 | Literature review: elderly gait analysis / fall-risk prediction papers and datasets | Short literature summary -- also feeds the still-outstanding Phase 1 literature matrix | - | Not Started
Week 1 | Data-availability assessment: usable public gait dataset vs. need for new recording -- decide FAST, this gates weeks 2-3 | Written data strategy decision. CONTINGENCY: if data looks thin, cut scope to 1-2 signals (e.g. walking speed + sit-to-stand time) rather than all 4 | Literature review | Not Started
Week 2 | Define the risk-score output contract: assess_risk(window) -> {risk_score, signals} | Documented interface, deliberately NOT a fall/no-fall flag | Data decision | Not Started
Week 2 | Implement src/gait/gait_features.py AND src/gait/gait_risk.py (first-pass rule-based model) -- compressed from two separate weeks in v1 | Working GaitRiskAssessor on whatever data is available | Interface defined | Not Started
Week 3 | Validate on available data; be explicit about how limited the validation is if data is thin | Honest validation write-up, limitations stated plainly | gait_risk.py | Not Started
Week 3 | Write up literature summary + findings for thesis material | Short report, shared with the team | All above | Not Started
Week 4 -- TESTING | Re-run validation on any additional data gathered during the month; confirm the risk score behaves sensibly on new inputs | Confidence the module isn't overfit to whatever small sample it was built against | Week 3 write-up | Not Started
Week 4 -- TESTING | Go through the Merge Checklist tab item by item | Signed-off checklist for this branch | - | Not Started
Week 4 -- TESTING | Participate in the cross-branch dependency smoke test | Confirms this module's dependencies don't conflict with TCN/YOLO's | All branches ready | Not Started

## Sync Points & Decisions
Sync Points & Decisions -- moments the team needs to talk, not just work solo
When | Sync Point / Decision | Who's Involved | Why It Matters
Start of Week 1 | Kickoff: confirm each person's branch scope, confirm the 'no shared-file edits' rule | All three | This is the single thing that keeps three parallel branches mergeable -- get explicit agreement before code starts
End of Week 1 | GAIT-specific check-in: is the data-availability assessment workable within the remaining 2 weeks, or does scope need to shrink now? | Hussain + team | This is the highest-risk decision point in the compressed timeline. Deciding to cut scope in Week 1 is far cheaper than discovering the same problem in Week 3 with no time left to react
End of Week 2 | Mid-point check-in: share early numbers/findings from each branch | All three | Catches a branch quietly off-track while there's still a week of implementation time left, not just testing-week time
End of Week 3 | All three implementation deliverables + first-pass write-ups due. TCN comparison results shared | All three | This is the compressed deadline -- everything that was 'Week 4' write-up work in v1 now has to land here so Week 4 is free for testing
During Week 4 | Testing week: each branch validated independently (see each Tasks tab), then the cross-branch dependency smoke test run together | All three | Confirms not just 'does my branch work' but 'do all three branches coexist in one environment' before anyone tries to merge
End of Week 4 | LSTM vs TCN final decision made | All three, ideally with advisor input | Locks in the temporal model the eventual structured event schema will reason over
End of Week 4 | Each branch formally checked against the Merge Checklist tab | Branch owner + one reviewer | Confirms no shared files were touched and Testing/ validation still passes before merging into main
End of Week 4 | Integration phase planned (not started) for the following month | All three | Per docs/IMPLEMENTATION_PLAN.md Section 5: wiring YOLO + the chosen temporal model + gait into the live pipeline is its own later, one-person-at-a-time phase

## Merge Checklist
Merge Checklist -- definition of done, run for real during Week 4
Checklist Item | TCN_sanawar | YOLO_fatima | GAIT_hussain
New code lives in a new module/folder only -- no edits to pipeline_utils.py, src/posture/lstm/*, hybrid_evaluate.py, evaluate_real_footage.py, or realtime_fall_detection.py | Not Started | Not Started | Not Started
python -m unittest tests.test_lstm_pipeline -v still passes | Not Started | Not Started | Not Started
No regression on hybrid_evaluate.py --batch_dir "Testing/Sanawar Testing 7-22-26" vs. results/hybrid_extended_window/ | Not Started | Not Started | Not Started
Short markdown write-up completed (style of docs/LSTM_Phase_Summary.md / context.txt) | Not Started | Not Started | Not Started
Branch synced with main periodically (git merge main), not left to diverge for weeks | Not Started | Not Started | Not Started
Branch-specific deliverable complete (see '<Branch> Tasks' tab, Week 3 rows) | Not Started | Not Started | Not Started
Week 4 validation complete: full re-test against Testing/, not just the dev sample | Not Started | Not Started | Not Started
Cross-branch dependency smoke test passed (no environment conflicts with the other two branches) | Not Started | Not Started | Not Started

## Risks & Blockers
Risks & Blockers -- log as soon as you notice one, not at the end
Branch | Risk | Likelihood / Impact | Mitigation | Status
All branches | 3-week implementation window is tighter than the original 4-week plan -- less slack if anything goes wrong | Medium / Medium | Week 1 and Week 2 check-ins exist specifically to catch slippage early, while there's still implementation time left to react | Open
GAIT_hussain | No existing dataset (UR Fall, UP-Fall, LeFD) supports gait/fall-risk analysis -- all are short single-fall-event clips. Losing a week of buffer makes this the highest-risk item in the whole plan | High / High | Data-availability assessment happens in Week 1, not later. CONTINGENCY: if data is thin, cut scope to 1-2 signals (walking speed, sit-to-stand time) rather than all 4 -- decide this explicitly in the Week 1 check-in, don't let it slip silently | Open
GAIT_hussain | Validation ends up thin given data scarcity, compounded by the shorter timeline | Medium / Medium | State limitations plainly in the write-up rather than overclaiming -- consistent with how the rest of this project has reported results | Open
TCN_sanawar | TCN architecture doesn't match LSTM's parameter budget, making comparison feel unfair | Medium / Low | Report the actual difference honestly rather than forcing a match -- the Continuation Plan explicitly wants parameter count reported because it's expected to differ | Open
YOLO_fatima | Running MediaPipe + YOLO together roughly doubles per-frame compute cost | High / Medium | Measure honestly in Week 2; if too slow for the eventual Jetson target, that's real information for the team, not a reason to hide the number | Open
YOLO_fatima | Generic COCO classes are a poor proxy for real medicine containers / pill organizers | High / Medium | Treat as a data problem, not a modeling problem -- scope out a custom dataset need explicitly rather than forcing COCO classes to work | Open
All branches | A branch quietly edits a shared file (pipeline_utils.py, hybrid_evaluate.py, etc.) to make something 'just work' during development | Medium / High | Merge Checklist item 1 exists specifically to catch this -- check it explicitly during Week 4, don't assume | Open